## Slide 1
MESA Operations

## Slide 2: Operations Subcommittee Report
Follow-up calls
Exam 6
  Core and Ancillary Study Progress
  Alerts
  Results Reporting
  CT Report
    Radiation Exposure
    Protocol Violations
Participant Relations Committee

## Slide 3: Follow-up Call Retention
Retention = Completed / (Enrolled – Dead)
Chart: 
| FU1 | FU2 | FU3 | FU4 | FU5 | FU6 | FU7 | FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17 | FU18
Done | 0.98 | 0.97 | 0.94 | 0.95 | 0.91 | 0.92 | 0.9 | 0.91 | 0.88 | 0.77 | 0.85 | 0.85 | 0.84 | 0.84 | 0.83 | 0.62 | 0.82 | 0.58

## Slide 4: Follow-up Retention by Ethnicity
Retention = Completed / (Enrolled – Dead) except FU 15 (windowed)
Chart: All Sites
| FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 96 | 87 | 92 | 90 | 87 | 88 | 87 | 70 | 88
A-A | 89 | 78 | 86 | 84 | 82 | 83 | 80 | 54 | 77
Hisp. | 86 | 69 | 83 | 78 | 77 | 76 | 78 | 53 | 76
Chin. | 95 | 83 | 84 | 85 | 86 | 84 | 83 | 67 | 83
Notes: done

## Slide 5: Follow-up Retention by Site
Chart: Minnesota
| FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 99 | 94 | 93 | 90 | 90 | 89 | 94 | 80 | 93
Hisp. | 88 | 75 | 82 | 78 | 79 | 70 | 82 | 47 | 80
Chart: NWU
| FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 97 | 80 | 90 | 91 | 89 | 88 | 88 | 66 | 89
A-A | 92 | 68 | 82 | 86 | 83 | 84 | 82 | 56 | 82
Chin. | 98 | 87 | 96 | 93 | 93 | 92 | 91 | 84 | 89
Chart: UCLA
| FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 99 | 97 | 91 | 88 | 89 | 88 | 90 | 83 | 88
A-A | 86 | 90 | 83 | 82 | 84 | 84 | 78 | 67 | 77
Hisp. | 88 | 85 | 81 | 71 | 72 | 72 | 71 | 59 | 71
Chin. | 91 | 81 | 78 | 82 | 82 | 80 | 78 | 57 | 83
Chart: WFU
| FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 95 | 94 | 90 | 92 | 89 | 91 | 82 | 61 | 87
A-A | 90 | 90 | 89 | 89 | 88 | 86 | 82 | 40 | 82
Chart: Columbia
| FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 90 | 58 | 90 | 90 | 87 | 89 | 88 | 70 | 86
A-A | 83 | 50 | 81 | 83 | 83 | 85 | 83 | 58 | 79
Hisp. | 85 | 51 | 83 | 86 | 80 | 84 | 83 | 51 | 88
Chart: JHU
| FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 98 | 93 | 92 | 87 | 81 | 84 | 83 | 69 | 82
A-A | 91 | 86 | 89 | 79 | 76 | 77 | 77 | 60 | 70
Retention = Completed / (Enrolled – Dead) except FU 18 (windowed)
Notes: Cut and paste

## Slide 6: Follow-up 18 Completion by Site
Site Name | Total ppts | Contacts Made |  | Interviews Completed |  | Unable | Refused
Wake Forest | 798 | 279 | 35% | 245 | 31% | 26 | 7
Columbia | 841 | 376 | 45% | 341 | 41% | 34 | 1
Hopkins | 708 | 431 | 61% | 379 | 54% | 46 | 2
Minnesota | 819 | 510 | 62% | 470 | 57% | 38 | 1
NWU | 899 | 456 | 51% | 409 | 46% | 39 | 6
UCLA | 958 | 399 | 42% | 335 | 35% | 60 | 1
Total | 5023 | 2451 | 49% | 2179 | 43% | 243 | 18
Includes only active (no study drop outs) participants, regardless of contact window.

## Slide 7: Follow-up
FU17 Ended August 14, 2016
  Asks participants for permission to send letter or brochure to MESA Contacts to inform them about MESA and their role as a Contact.
FU18 Started August 15, 2016
  Scheduled Exam 6 and asks participants stroke symptom and medical literacy questions.
FU19 Scheduled to start August 15, 2017
  Proposals for new follow-up questions are being collected for review in early May
Notes: FU 16 started October 2014
  Ended 7 months early in August 2015 to accommodate new MESA 3 FU schedule (one FU call per year, starting and ending in August)
  Includes medications inventory, new questions for gout, food security, e-cigarette use, blood thinner/anticoagulant use

## Slide 8: Exam 6 Completion
Chart: 
As of 4/9/2017, 1413 participants completed Exam 6 core exam. Retention is currently at 90% of the target.

## Slide 9: Exam 6 Completion
Chart: WFU
Chart: COL
Chart: JHU
Chart: UMN
Chart: NWU
Chart: UCLA

## Slide 10: Exam 6 Core Exam
#Participants | ~ 4000 PPTs.
Time Burden | Average duration: 90 minutes
Exam components | Consent/Check-in Seated blood pressure, pulse oximetry Anthropometry Phlebotomy Medical history (SF-12, PROMIS Physical Function) Personal history/demographics Medication Inventory

## Slide 11: Exam 6 Core Completion
Study | Component | Goal | Selected with E6 Visit | Complete | %Complete (of selected w/E6 Visit)
Core | Blood Pressure | 4000 | 1413 | 1410 | 100%
 | Oximetry | 4000 | 1413 | 1409 | 100%
 | Anthropometry | 4000 | 1413 | 1409 | 100%
 | Phlebotomy | 4000 | 1413 | 1354 | 96%
 | Urine | 4000 | 1413 | 1346 | 95%
 | Medications | 4000 | 1413 | 1410 | 100%
 | Medical History | 4000 | 1413 | 1409 | 100%
 | Personal History | 4000 | 1413 | 1403 | 99%
 | Physical Function | 4000 | 1413 | 1400 | 99%

## Slide 12: Exam 6 Ancillary Study Completion
Study | Component | Goal | Selected with E6 Visit | Complete | %Complete (of selected w/E6 Visit)
Heart Failure | Echo | 4000 | 1413 | 1356 | 96%
 | Arterial Stiffness | 4000 | 1413 | 1341 | 95%
 | Physical Activity | 4000 | 1413 | 1400 | 99%
 | KCCQ-12 | 4000 | 1413 | 1400 | 99%
 | 6MW | 4000 | 1413 | 1183 | 84%
UKNOW | Urinary Symptoms | 4000 | 1413 | 1398 | 99%
Notes: *Epi of Athero and MESA INVITE Ancillary Studies started just recently; selected participants will return to clinic to complete
exam components.
**Participants who are selected and ineligible for Lung CT with contrast are considered for Lung CT w/o contrast.

## Slide 13: Exam 6 Ancillary Study Completion
Study | Component | Goal | Selected with E6 Visit | Complete | %Complete (of selected w/E6 Visit)
MESA Lung/Lung NS | CT (any) | 2950 | 1327 | 799 | 60%
 | w/Contrast | 1000 | 859 | 258 | 30%
 | Spirometry | 2950 | 1293 | 1108 | 86%
 | Lung Questionnaire | 2950 | 1293 | 1100 | 85%
Athero | Carotid US | 1892 | 650* | 63 | 10%
Notes: *Epi of Athero and MESA INVITE Ancillary Studies started just recently; selected participants will return to clinic to complete
exam components.
**Participants who are selected and ineligible for Lung CT with contrast are considered for Lung CT w/o contrast.

## Slide 14: Exam 6 Ancillary Study Completion
Study | Component | Goal | Selected with E6 Visit | Complete | %Complete (of selected w/E6 Visit)
Afib | HM Patch applied | 1500 | 1061 | 658 | 62%
 | Cog Func Testing | 1500 | 1061 | 654 | 62%
MESA Memory | Cog Func Testing | 432 | 126 | 62 | 49%
 | Brain MRI | 432 | 126 | 31 | 25%
 | Amyloid PET | 216 | 126 | 5 | 4%
INVITE | Drug Dispensed | 1600 | 192 | 38 | 20%
Notes: *Epi of Athero and MESA INVITE Ancillary Studies started just recently; selected participants will return to clinic to complete
exam components.
**Participants who are selected and ineligible for Lung CT with contrast are considered for Lung CT w/o contrast.

## Slide 15: Exam 6 Alerts
Site | Wake | Col | JHU | Minn | NWU | UCLA | Total
Oximetry Complete | 136 | 204 | 202 | 310 | 316 | 241 | 1409
Oximetry Alert | 0 | 3 | 2 | 1 | 1 | 0 | 7
BP Complete | 135 | 205 | 203 | 310 | 316 | 241 | 1410
BP Alert | 2 | 3 | 9 | 5 | 2 | 2 | 23
Echo Complete | 120 | 200 | 189 | 280 | 309 | 192 | 1290
Echo Read Complete | 120 | 163 | 149 | 224 | 243 | 193 | 1092
Echo Alerts | 0 | 5 | 3 | 3 | 2 | 2 | 15
Heart Monitor Applied | 63 | 51 | 78 | 157 | 97 | 126 | 572
Heart Monitor Safety Read (2 per ppt) | 65 | 111 | 119 | 252 | 184 | 122 | 853
Heart Monitor Alert | 3 | 3 | 3 | 6 | 10 | 5 | 30
Lipids Data Received | 114 | 169 | 158 | 267 | 267 | 206 | 1181
Lipids Alert | 1 | 1 | 2 | 1 | 3 | 3 | 7
Notes: Karen to update Lung CT Alerts

## Slide 16: Lung CT Alerts
  Local Reading: Johns Hopkins and Northwestern
  Central Reading (at Columbia): Wake Forest, Columbia, Minnesota, and UCLA
Site | CT Complete | Lung Safety Read Done (% complete) | Number of Reads Outstanding > 4 weeks | Lung CT Alerts
3: Wake Forest | 46 | 42 (91%) | 0 | 1
4: Columbia | 127 | 98 (77%) | 11 | 11
5: Hopkins | 162 | 161 (~100%) | 3 | 29
6: Minnesota | 277 | 254 (92%) | 9 | 23
7: Northwestern | 190 | 190(~100)* | n/a | 42
8: UCLA | 17 | 7 (41%) | 4 | 0
Total | 819 | 752(92%) | 27 | 106

## Slide 17: Exam 6 Results Reporting
Procedure | Count | Minimum | 25th Percentile | Median | 75th Percentile | Maximum
Lab Assays | 1181 | 3 | 29 | 34 | 49 | 94
Spirometry | 590 | 2 | 47 | 60 | 71 | 143
Echo | 816 | 18 | 51 | 68 | 82 | 142
Heart Monitor Patch | 205 | 34 | 54 | 68 | 88 | 150

## Slide 18: CT Report

## Slide 19: Total CT Radiation to Date vs Approved Limits
Each site has a consented dose of 6.5mSv
Average Total Dose per Subject
  Contrast Subjects at Force sites: ~4.39 mSv
  Contrast Subjects at Flash sites: ~2.53 mSv
  Non-Contrast Subjects at Force sites: ~2.33 mSv
  Non-Contrast Subjects at Flash sites: ~3.11 mSv
Notes: Additional Exclusions:
Lung CT with contrast exclusions:
Latest BMI > than 35
Latest eGFR < than 60
Has pacemaker or defibrillator
Enrolled in COPD2
Selected for Late COPD2
Lung CT w/o contrast exclusions:
Selected for Late COPD2
Selected for & completes Exam 6 lung CT with contrast
Completed COPD2 chest CT
PET (Columbia) exclusions:
Age < 60 or > 90 years
Carotid plaque documented by ultrasound
Weight > 300 lbs (scanner limit)
Metal implant incompatible with MRI scanning
Physical or cognitive impairment that would prevent giving consent or completing the PET-MRI procedure
insulin use for treatment of diabetes (because of challenges in performing the PET-MRI scan in the fasting state)
Cumulative radiation >20 mSv of radiation from CT scans in MESA over the duration of the study (approximately 5% of the cohort),
Amyloid-PET (Wake) exclusions:
TBD – Mainly cumulative radiation > 20 mSV
Per Tim Hughes: Estimated radiation = 3.5 mSv

## Slide 20: Cumulative Radiation to Date
Maximum Radiation Limit for a participant on study from Exam 1 – Exam 6 ~32 mSv.
No participants have reached this maximum
Site | Valid N | Mean (mSv) | Standard Deviation | Minimum | 25th Percentile | Median | 75th Percentile | Maximum
Wake | 1079 | 11.45 | 4.91 | 2.40 | 7.48 | 11.20 | 14.75 | 24.60
Columbia | 1095 | 7.70 | 4.42 | 1.20 | 2.80 | 7.83 | 10.57 | 22.97
Hopkins | 1089 | 7.35 | 4.35 | 1.80 | 3.75 | 6.14 | 10.28 | 23.13
Minnesota | 1064 | 8.50 | 4.30 | 1.80 | 4.75 | 7.94 | 11.79 | 20.84
NWU | 1157 | 6.94 | 3.92 | 1.20 | 2.40 | 6.86 | 9.72 | 21.90
UCLA | 1330 | 5.76 | 3.81 | 1.20 | 1.40 | 4.93 | 8.69 | 18.12
All Sites | 6814 | 7.85 | 4.63 | 1.20 | 3.71 | 7.50 | 10.89 | 24.60

## Slide 21: Protocol Violations
2 high-level protocol violations (both reported to OSMB, IRBs)
  JHU – Total dose ended up 8.07 mSv
  WFU – Subject was scanned with contrast although eGFR was below 60 (58)
Low-level protocol violations
  1 total subject – Scan was performed but data is unavailable
  3 total subjects - Incorrect Protocol Used (total dose did not exceed consented dose; scans usable)
  33 total subjects - Scans started more than 2cm above apices or ended more than 5cm past base of lung (total dose did not exceed consented dose)

## Slide 22: Conclusions
Exam 6 generally going well
Reading times improving
Need to plan for home visit
  Ancillary study components?
Thank your coordinators!

## Slide 23: Participant Relations Committee
Letters to MESA Contacts
  FU17 asks permission from participants to send letter or brochure to MESA Contacts (also added as an Exam 6 ICF item)
  Letter is currently under IRB review
Participant Website Updates
  Spanish/Chinese translations now available for main participant webpages
  Article summaries and press releases are added monthly

## Slide 24: Participant Relations Committee
Newsletter
  Mail in January 2017
  Articles include
    Precision Medicine initiative
    Sleep disturbances and health
    Detection of damaged heart muscle using MRI
  Next newsletter planned for June 2017
  One newsletter per year planned for remainder of MESA 3 contract