## Slide 1
Exam 7 Plans and Preparation
June 29, 2020

## Slide 2: Outline
Timeline
Core Exam Components
Ancillary Study Proposals

## Slide 3: Timeline

## Slide 4: Timeline

## Slide 5: Timeline
Exam 7 AS/Grant proposals
  Grant Proposals submissions Oct/Nov 2020
    1st/only
    2nd submissions
  Ancillary Study proposals submissions due August 2020

## Slide 6: Timeline
Exam 7 Prep Jan–Oct 2021
  Essential documents, Authorizations, …
    Task Area B proposals/budget
    Protocol January – March (Design Committee)
    Operations Manual (Clinical Operations)
    sIRB
    OSMB Review
  Programming
  Site preparation (Hiring, training, certification, …)
  Central Training
  Pilot

## Slide 7: Timeline (suggested)

## Slide 8: Timeline
Exam conduct 18 months
  Oct 19, 2021 - Apr 18, 2023
Exam Closeout 3 months
  Apr 19 – July 18, 2023

## Slide 9: Exam 7 Core Parameters
3,000 target
 | Exam 7 Estimate (2022 CY)
3: WFU | 475 (15.8%)
4: COL | 530 (17.7%)
5: JHU | 410 (13.6%)
6: UMN | 505 (16.8%)
7: NWU | 555 (18.6%)
8: UCLA | 525 (17.6%)
Total | 3,000 (100%)

## Slide 10: Exam 7 Core Parameters
Emphasis on retention
  Suggested approach: Participant Chooses how much they want to do
  Complete everything possible outside of the clinic
    phone, online, mail, home, …
Total time commitment <8 hrs
  Core Exam ~90 minutes
  Ancillary studies have added ~30-90 minutes each (based on Exam 5 and 6)

## Slide 11: Exam 7 Core components
Reception and consent
Anthropometry
Blood pressure
Specimen collection and lab processing
  Blood volume 70mL total
    chol, glucose, A1c, creatinine, AS, QC, Repository, …
  Spot Urine collection
    creatinine, albumin

## Slide 12: Exam 7 Core components
Medical History
Personal History
Health and Life
Medications
Physical Activity
FFQ/Diet?

## Slide 13: Exam 7 Ancillary Components
Follows Exam 5 & 6 Model
Ancillary Studies -> exciting science
Single integrated Exam
Avoid delayed or “soft” start

## Slide 14: Exam 7 Ancillary Component Highlights (Proposed)