## Slide 1
MESA Operations
Subcommittee Report

## Slide 2: Operations Subcommittee Report
Timeline
Follow-up calls / Retention
Exam 6
Participant Relations Committee

## Slide 3: MESA 3 Timeline
Exam 6 Sept 6, 2016 – March 30, 2018
Annual Follow-up phone calls run congruent with fiscal years

## Slide 4: Follow-up Calls
Follow-up 16
  Ended 7 months early in August 2015
  Medications inventory, new questions for gout, food security, e-cigarette use, blood thinner/anticoagulant use
Follow-up 17
  Started August 2015 (60% complete)
  New MESA 3 follow-up schedule
  Permission to send letter to Contacts with information about MESA and role as a Contact
Notes: Add new unique FU17 questions

## Slide 5: Follow-up Call Retention
Retention = Completed / (Enrolled – Dead)
Chart: 
85%
Chart: 
| FU1 | FU2 | FU3 | FU4 | FU5 | FU6 | FU7 | FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
Done | 0.98 | 0.97 | 0.94 | 0.95 | 0.91 | 0.92 | 0.9 | 0.91 | 0.88 | 0.77 | 0.85 | 0.85 | 0.84 | 0.84 | 0.83 | 0.61 | 0.67

## Slide 6: Follow-up Retention by Ethnicity
Chart: All Sites
| FU7 | FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 95 | 97 | 96 | 87 | 92 | 90 | 87 | 88 | 87 | 70 | 77
A-A | 91 | 93 | 89 | 78 | 86 | 84 | 82 | 83 | 80 | 54 | 61
Hisp. | 89 | 90 | 86 | 69 | 83 | 78 | 77 | 76 | 78 | 53 | 58
Chin. | 95 | 95 | 95 | 83 | 84 | 85 | 86 | 84 | 83 | 67 | 60
Retention = Completed / (Enrolled – Dead) except FU 17 (windowed)
85%
Notes: done

## Slide 7: Follow-up Retention by Site
Chart: JHU
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 99 | 98 | 93 | 92 | 87 | 81 | 84 | 83 | 69 | 68
A-A | 92 | 91 | 86 | 89 | 79 | 76 | 77 | 77 | 60 | 54
Retention = Completed / (Enrolled – Dead) except FU 17 (windowed)
85%
85%
Chart: WFU
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 96 | 95 | 94 | 90 | 92 | 89 | 91 | 82 | 61 | 70
A-A | 96 | 90 | 90 | 89 | 89 | 88 | 86 | 82 | 40 | 67
Chart: Columbia
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 94 | 90 | 58 | 90 | 90 | 87 | 89 | 88 | 70 | 77
A-A | 89 | 83 | 50 | 81 | 83 | 83 | 85 | 83 | 58 | 63
Hisp. | 90 | 85 | 51 | 83 | 86 | 80 | 84 | 83 | 51 | 60
Chart: Minnesota
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 98 | 99 | 94 | 93 | 90 | 90 | 89 | 94 | 80 | 87
Hisp. | 90 | 88 | 75 | 82 | 78 | 79 | 70 | 82 | 47 | 62
Chart: NWU
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 97 | 97 | 80 | 90 | 91 | 89 | 88 | 88 | 66 | 81
A-A | 94 | 92 | 68 | 82 | 86 | 83 | 84 | 82 | 56 | 71
Chin. | 97 | 98 | 87 | 96 | 93 | 93 | 92 | 91 | 84 | 76
Chart: UCLA
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15 | FU16 | FU17
White | 99 | 99 | 97 | 91 | 88 | 89 | 88 | 90 | 83 | 82
A-A | 96 | 86 | 90 | 83 | 82 | 84 | 84 | 78 | 67 | 45
Hisp. | 89 | 88 | 85 | 81 | 71 | 72 | 72 | 71 | 59 | 54
Chin. | 93 | 91 | 81 | 78 | 82 | 82 | 80 | 78 | 57 | 52
Notes: Cut and paste

## Slide 8: Follow-up 17 Completion by Site
Site Name | Follow-up Due | Contacts Made |  | Interviews Completed |  | Unable | Refused
Wake Forest | 436 | 384 | 88% | 320 | 73% | 53 | 10
Columbia | 437 | 373 | 85% | 321 | 73% | 47 | 5
Hopkins | 388 | 370 | 95% | 328 | 85% | 40 | 1
Minnesota | 448 | 426 | 95% | 378 | 84% | 44 | 4
NWU | 501 | 487 | 97% | 432 | 86% | 50 | 5
UCLA | 521 | 449 | 86% | 370 | 71% | 77 | 1
Total | 2731 | 2489 | 91% | 2149 | 79% | 311 | 26
Completed = Completed / (Enrolled – Dead – Dropped)
Notes: UPDATE. % of FU complete does not include drop outs.

## Slide 9: Retention
Follow-up 16
  Low (expected/truncated)
Follow-up 17
  All sites behind schedule
  Particularly among minority groups
  Important to focus on call completion now
  “Limited” call (contacts, events) available
Notes: Add new unique FU17 questions

## Slide 10: Operations Subcommittee Report
Timeline
Follow-up calls / Retention
Exam 6
Participant Relations Committee

## Slide 11: Exam 6
No longer: MESA Classic Exam (ancillaries)
Now: MESA Exam 6 = Core + Ancillaries
(particularly for ancillaries at all sites)

## Slide 12: Exam 6 Preparation Timeline

## Slide 13: Exam 6 Preparation Timeline

## Slide 14: Exam 6 Core
#Participants | ~ 4000 ppts
Time Burden | Average duration: 90 minutes
Exam components | Consent/Check-in Seated blood pressure, pulse oximetry Anthropometry Phlebotomy Medical history (SF-12, PROMIS Physical Function) Personal history/demographics Medication Inventory

## Slide 15: Exam 6 Ancillary Studies
PI | Sample | Title
Bertoni, Shah | All | Transition from risk factors to early HF
Barr | 2000 (All sites) | Pulmonary microvascular perfusion in MESA
Smith | 650 (All sites) | COPD in non-smokers
Heckbert | 1500 (All sites) | Atrial fibrillation & vascular disease of the brain
Hughes, Craft | 550 (Wake) | Cardiometabolic risk for Alzheimer's
Shea | 350 (CU) | HDL-mediated cholesterol efflux and carotid FDG PET

## Slide 16: Exam 6 Components (~Day 1)
 | Time | Sample | Main or Ancillary
Reception/Consent | 15 | All | Main
Change Clothes | 5 | All | Main
Blood Pressure | 15 | All | Main
Pulse Oximetry | 0 | All | Main
Anthropometry | 10 | All | Main
Phlebotomy | 15 | All | Main
Urine Collection | 5 | All | MESA HF
Snack |  | All | Main
Echocardiography | 25 | All | MESA HF
Arterial Tonometry | 5 | All? | MESA HF
Spirometry | 20 | 2650 | MESA Lung/NonSmk
Lung CT | 30 | 2650 (1000 w/ contrast) | MESA Lung NonSmk
6 Minute Walk Test | 15 | All | MESA HF
Patch Application | 15 | 1500 | MESA AF

## Slide 17: Exam 6 Questionnaires (~Day 1)
 | Time | Sample | Main or Ancillary
Medications | 10 | All | Main
Medical History | 10 | All | Main
Personal History | 5 | All | Main
Physical Activity | 15 | All | Main
HF Symptoms/Risk | 25 | All | MESA HF
Physical Activity | 15 | All | MESA HF
COPD Scores | 20 | 2650 | MESA Lung/NonSmk
Cognitive Function | 35 | 1500 | MESA AF
Additional Cognitive Function | 95 | 540 | Cognitive Function Testing
Patch Application | 15 | 1500 | MESA AF

## Slide 18: Exam 6 – Other Visits
 | Time | Sample | Main or Ancillary
Lung CT | 30 | 2650 | MESA Lung/NonSmk
Brain MRI | 35 | 1500 | MESA AF
Carotid PET | 95 | 540 | Cognitive Function Testing
Patch Application | 15 | 1500 | MESA AF

## Slide 19: Exam 6 Status
Consent Template
  Reviewed by Steering, Operations, E6 Consent Committees
  Current draft posted on MESA E6 Planning webpage
Forms and Content Committee is finalizing:
  Study Questionnaires and completion forms
  FU18 form packet

## Slide 20: Exam 6 Status, ctd
High tech and lab results letters
  Main text for letters is drafted, ready for Ops/PRC review
  CC/Ops working with ancillary study PIs to understand reporting for specific tests/procedures
Safety reads for ECHO, CT

## Slide 21: Thank You!!!

## Slide 22: Participant Relations Committee
Letters to MESA Contacts
  FU17 asks permission from participants to send letter or brochure to MESA Contacts (also added as an Exam 6 ICF item)
  PRC drafted letter to inform MESA Contacts of their role in MESA
Participant Website Updates
  Spanish/Chinese translations now available for main participant webpages
  Article summaries and press releases are added monthly

## Slide 23: Participant Relations Committee
Newsletter
  Mail in June 2016
  Announces Exam 6 and planned ancillary study components
  Next newsletter planned for November 2016
  One newsletter per year planned for remainder of MESA 3 contract