## Slide 1
MESA Operations
Subcommittee Meeting

## Slide 2: Operations Subcommittee Report
Retention
Follow-up calls
Participant Communications
Ongoing Ancillary Studies
Notes: Update for Feb 2014

## Slide 3: Follow-up Call Retention
Retention = Completed / (Enrolled – Dead)
Chart: 
| FU1 | FU2 | FU3 | FU4 | FU5 | FU6 | FU7 | FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
Done | 0.98 | 0.97 | 0.94 | 0.95 | 0.91 | 0.92 | 0.9 | 0.91 | 0.88 | 0.77 | 0.85 | 0.85 | 0.84 | 0.83 | 0.8
85%
Notes: Done. Final FU13 retention is 84%, FU14 is 83%, FU15 is 80%

## Slide 4: Follow-up Retention by Ethnicity
Retention = Completed / (Enrolled – Dead) except FU 15 (windowed)
Chart: All Sites
| FU7 | FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
White | 95 | 97 | 96 | 87 | 92 | 90 | 87 | 88 | 87
A-A | 91 | 93 | 89 | 78 | 86 | 84 | 82 | 83 | 76
Hisp. | 89 | 90 | 86 | 69 | 83 | 78 | 77 | 76 | 69
Chin. | 95 | 95 | 95 | 83 | 84 | 85 | 86 | 84 | 78
85%
Notes: done

## Slide 5: Follow-up Retention by Site
Retention = Completed / (Enrolled – Dead) except FU 14 and 15 (windowed)
Chart: WFU
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
White | 96 | 95 | 94 | 90 | 92 | 89 | 91 | 84
A-A | 96 | 90 | 90 | 89 | 89 | 88 | 86 | 80
Chart: Columbia
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
White | 94 | 90 | 58 | 90 | 90 | 87 | 89 | 86
A-A | 89 | 83 | 50 | 81 | 83 | 83 | 85 | 69
Hisp. | 90 | 85 | 51 | 83 | 86 | 80 | 84 | 66
Chart: JHU
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
White | 99 | 98 | 93 | 92 | 87 | 81 | 84 | 81
A-A | 92 | 91 | 86 | 89 | 79 | 76 | 77 | 74
Chart: Minnesota
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
White | 98 | 99 | 94 | 93 | 90 | 90 | 89 | 90
Hisp. | 90 | 88 | 75 | 82 | 78 | 79 | 70 | 72
Chart: NWU
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
White | 97 | 97 | 80 | 90 | 91 | 89 | 88 | 89
A-A | 94 | 92 | 68 | 82 | 86 | 83 | 84 | 86
Chin. | 97 | 98 | 87 | 96 | 93 | 93 | 92 | 86
Chart: UCLA
| FU8 | FU9 | FU10 | FU11 | FU12 | FU13 | FU14 | FU15
White | 99 | 99 | 97 | 91 | 88 | 89 | 88 | 88
A-A | 96 | 86 | 90 | 83 | 82 | 84 | 84 | 71
Hisp. | 89 | 88 | 85 | 81 | 71 | 72 | 72 | 70
Chin. | 93 | 91 | 81 | 78 | 82 | 82 | 80 | 72
85%
Notes: Cut and paste

## Slide 6: Lower Retention among Hispanics
Possible reasons
  Emigration
  Difficulty reaching/searching in home countries
  Movement of all contacts
  ?occult deaths
Approaches
  Continued efforts in home countries
  Discuss approaches with HCHS
  Possible contacts w/ DOH in Mexico, DR, PR?
Notes: Update/Remove for Sept 2014

## Slide 7: Follow-up 14 Completion (Overall)
Site | Window Closed Interview Done | All Interviews Done | % of FU14 Completed
WFU | 781 | 783 | 89%
Col | 767 | 846 | 94%
JHU | 700 | 739 | 93%
Minn | 756 | 759 | 85%
NWU | 854 | 935 | 97%
UCLA | 921 | 1026 | 99%
TOTAL | 4779 | 5088 | 93%
Notes: Done. % of FU complete does not include drop outs.

## Slide 8: Follow-up 14 Completion by Site
Notes: Done. % of FU complete does not include drop outs.

## Slide 9: Follow-up 15 Completion (Overall)
Site | Window Closed Interview Done | All Interviews Done | % of FU14 Completed
WFU | 320 | 332 | 38%
Col | 263 | 402 | 45%
JHU | 290 | 361 | 47%
Minn | 322 | 419 | 48%
NWU | 357 | 471 | 50%
UCLA | 387 | 664 | 65%
TOTAL | 1939 | 2649 | 49%
Notes: Done. % of FU complete does not include drop outs.

## Slide 10
 | Target | Interview Done | Complete
MESA Air – Recruited from MESA Family |  |  | 
Wake Forest | 40 | 40 (100%) | 40 (100%)
Columbia | 134 | 134 (100%) | 105 (78%)
Johns Hopkins | 43 | 43 (100%) | 35 (81%)
Minnesota | 77 | 77 (100%) | 56 (73%)
Northwestern | 143 | 143 (100%) | 113 (79%)
UCLA | 16 | 16 (100%) | 13 (81%)
MESA Air New Recruits |  |  | 
Columbia | 94 | 94 (100%) | 86 (91%)
UCLA | 149 | 149 (100%) | 137 (92%)
Follow-up 14 – Air/Family Participants
Notes: Done.

## Slide 11: Follow-up Retention
F/U 14 will finish in October 2014 (93% done)
  Includes Medications Inventory and Residential History Review
F/U 15 started January 2014 (49% done)
  Heterogeneity across sites in startup and completion rates
  No Medications Inventory or Residential History Review.
FU 16 will start October 2015
  Includes Medications Inventory, new questions for gout, food security, e-cigarette use, blood thinner/anticoagulant use
Notes: EDIT?

## Slide 12: Newsletter
Mailed in July
Reformatted for greater participant appeal:
  Full color
  More graphics and pictures
  More white space
  Articles contained on a single page if possible, no skipping pages to continue
Next newsletter planned for early 2015
Notes: done

## Slide 13: Ancillary Studies
MESA Air?
MESA COPDII

## Slide 14: Thank You!!!