## Slide 1
MESA Operations
Subcommittee Meeting

## Slide 2: Operations Subcommittee Report
Retention
Follow-up calls
  F/U 13 progress
  Approaching to hit 85% in F/U 13
  Starting F/U 14
MESA Air Report
Participant Communications
Notes: Updated for April 2013

## Slide 3: Follow-up Call Retention
Retention = Completed / (Enrolled – Dead)
Notes: New for April, 2013

## Slide 4: Follow-up Retention by Ethnicity
Retention = Completed / (Enrolled – Dead) except FU 13 (windowed)
Chart: Retention Rate
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU12 | FU13
White | 95 | 97 | 96 | 87 | 92 | 89 | 85
A-A | 91 | 93 | 89 | 77 | 86 | 83 | 77
Hisp. | 89 | 90 | 86 | 69 | 83 | 76 | 70
Chin. | 94 | 94 | 94 | 83 | 84 | 85 | 84
Notes: Updated for April – Includes FU13 for all participants with closed windows (including study dropouts)

## Slide 5: Followup Retention by Site
Chart: WFU
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 95 | 97 | 95 | 95 | 91 | 93 | 69
A-A | 92 | 97 | 90 | 90 | 89 | 89 | 58


Chart: Columbia
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 94 | 94 | 90 | 58 | 90 | 86 | 80
A-A | 88 | 88 | 84 | 50 | 82 | 80 | 70
Hisp. | 91 | 90 | 85 | 52 | 84 | 82 | 59
Chart: JHU
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 97 | 98 | 97 | 93 | 92 | 86 | 86
A-A | 91 | 93 | 92 | 86 | 88 | 78 | 85
Chart: Minnesota
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 91 | 97 | 98 | 95 | 94 | 89 | 90

Hisp. | 89 | 91 | 87 | 75 | 83 | 77 | 65
Chart: NWU
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 97 | 97 | 97 | 80 | 90 | 91 | 95
A-A | 95 | 94 | 92 | 68 | 82 | 86 | 96

Chin. | 96 | 97 | 98 | 86 | 95 | 93 | 98
Chart: UCLA
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 98 | 99 | 99 | 97 | 91 | 88 | 90
A-A | 92 | 95 | 86 | 90 | 84 | 79 | 77
Hisp. | 89 | 89 | 88 | 84 | 81 | 71 | 81
Chin. | 93 | 93 | 91 | 81 | 78 | 79 | 73
Retention = Completed / (Enrolled – Dead) except FU 13 (windowed)
Notes: Updated for April, 2013 – FU 13 added

## Slide 6: Follow-up 13 Expected* Closed Windows
Expected Contacts Made
3: Wake Forest 465 272 58%
4: Columbia 448 317 71%
5: Johns Hopkins 411 408 99%
6: Minnesota 460 391 85%
7: Northwestern 505 494 98%
8: UCLA 533 472 89%
* Study dropouts not included in these numbers
Notes: Updated for April, 2013

## Slide 7: Follow-up 13 Productivity
Site | Window Closed Interview Done | All Interviews Done | Additional interviews not reported in retention slide | % of FU13 Completed
WFU | 306 | 323 | 17 | 35%
Col | 319 | 481 | 162 | 50%
JHU | 364 | 443 | 79 | 47%
Minn | 378 | 496 | 118 | 52%
NWU | 489 | 536 | 47 | 51%
UCLA | 432 | 640 | 208 | 54%

## Slide 8
 | Target Cumulative | Completed Cumulative | Percent of Goal
MESA Air – Recruited from MESA Family |  |  | 
Wake Forest | 26 | 8 | 31%
Columbia | 87 | 6 | 7%
Northwestern | 88 | 75 | 85%
UCLA | 10 | 0 | 0%
Minnesota | 48 | 27 | 56%
Johns Hopkins | 28 | 24 | 86%
MESA Air New Recruits |  |  | 
UCLA | 91 | 0 | 0%
Columbia | 58 | 18 | 31%
Follow-up 13 – Air/Farmily Participants

## Slide 9: Follow-up Retention
F/U 12 finished
F/U 13
  Heterogeneity across sites improving
  MESA Air follow-up is on track for some sites and extremely behind for others  Need to finish by July 1
F/U 14 starting soon
  IRB approval received at three sites
  Will include medications inventory and residential history review
Notes: Updated for April, 2013

## Slide 10: Common Retention Obstacles
Declining cognitive function
Hearing loss
Aging, health issues, and life events require all available time and energy
Cultural and Immigration issues
Search options less effective with dropping of land lines
Insufficient number of contact people

## Slide 11: Approaches for 85%+ FU Retention
Revised Web Reports (for PIs and Coordinators) and Software Updates
Abbreviated FU call “Have you been hospitalized”
Letter/email asking the same
Systematic reexamination of “Dropped” ppts

## Slide 12: If money were no object……
Incentives and strategies:
  Informative breakfast or event
  Consider using social media to help find people
  Payment or gift card for completed interview
  Give certificates or reward milestones (e.g. specific # of FU)
  Send them to lunch/dinner at a nice restaurant
  Enter them into a drawing for a scooter or car
  Give them cell phones (with GPS)
  Create MESA app or game for cell phone

## Slide 13: Newsletter
Will be mailed in May
Translation underway
Reformatted for greater participant appeal:
  Full color
  More graphics and pictures
  More white space
  Articles contained on a single page if possible, no skipping pages to continue
Notes: Updated for April, 2013

## Slide 14: Thank You!!!