## Slide 1: Operations Subcommittee Report
Follow-up calls
  F/U 7 Final numbers
  F/U 8 Status
  F/U 9 Status
Exam 5
  Timelines
  Components / Participant Burden
“Gap” Incentives
Newsletter / website
Participant Relations Committee

## Slide 2: Follow-up 7 Retention by Site, Ethnicity
Overall 93%
Notes: ND – Updated 2/22/2008

## Slide 3: Follow-up 8 Retention by Site, Ethnicity
Overall 92%
Notes: ND – Updated 2/22/2008

## Slide 4: Follow-up 9
Pilot test of direct data entry completed
Follow-up 9 interviews are underway
Air Questionnaire built in
Data being received at CC
Weekly reports of data received sent to FCs

## Slide 5: Follow-up Calls in MESA II
Notes: ND - Moved white line

## Slide 6: Exam 5 Timeline
August 15, 2008 – August 14, 2009 | Protocol development
November 1, 2008 – November 30, 2009 | Software development
December 31, 2009 | Forms, consents, & results reports finalized
January 1, 2010 – January 31, 2010 | Translation of forms, consents, & results reports
February 1, 2010 | IRB submissions at sites
February, 2010 (2nd or 3rd week) | Central Training
March, 2010 (1st week) | Pilot Study
April 15, 2010 – September 15, 2011 | Exam 5
September 30, 2011 – October 31, 2011 | Closeout at FCs and final data check
Notes: No change

## Slide 7: Exam 5 Components and Timing
Maximum Total Hours 8.0

## Slide 8: “Gap Incentive”
Each FC to finalise gift/reminder during the Classic “Gap”

## Slide 9: Newsletter
English version done and at printer
Spanish and Chinese versions in final formatting
Spanish and Chinese to printer this week
All versions in homes this month

## Slide 10: Participant Website

## Slide 11: Participant Relations Committee
No meeting tonight
Purpose – Advocate for participants
  Reports; burden; other pt issues
Proposal composition
  Chair: Study coordinator
  Members: 1-2 investigators, PO, study coordinator
    ? Participants vs. Site-specific participant groups

## Slide 13: Agenda
1. Exam 4 Final Numbers
2. Follow-up calls
• F/U 7 Final numbers
• F/U 8 Status
• F/U 9 Status
3. Exam 5
• Timelines
• Components/Burden
4. Participant Relations Committee
• Membership
• Charges / Tasks
&#61692; Participant Results
&#61692; Participant Web site
&#61692; Newsletter
&#61692; Translations
&#61692; Other
5. Ancillary Studies – Impact on Exam 5
6. Newsletter
7. Other issues