## Slide 1
MESA Operations
Subcommittee Report

## Slide 2: Operations Subcommittee Meeting
Retention
Follow-up calls
  F/U 13 progress
    Currently at 82%; working to hit 85% in F/U 13
  F/U 14 underway
MESA Air Report
Participant Communications
Ancillary Studies Ongoing
Notes: Updated for Oct. 2013

## Slide 3: Follow-up Call Retention
Retention = Completed / (Enrolled – Dead)
Chart: 
| FU1 | FU2 | FU3 | FU4 | FU5 | FU6 | FU7 | FU8 | FU9 | FU10 | FU11 | FU12
Done | 0.97883 | 0.97186 | 0.93655 | 0.95241 | 0.91332 | 0.92225 | 0.89954 | 0.90902 | 0.88228 | 0.76837 | 0.84811 | 0.84466
Notes: Updated for October, 2013; New line added to show slope (visually, not mathematically!)

## Slide 4: Follow-up Retention by Ethnicity
Retention = Completed / (Enrolled – Dead) except FU 13 (windowed)
Chart: All Sites
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU12 | FU13
White | 95 | 97 | 96 | 87 | 92 | 90 | 85
A-A | 91 | 93 | 89 | 77 | 86 | 84 | 80
Hisp. | 89 | 90 | 86 | 69 | 83 | 78 | 77
Chin. | 94 | 94 | 94 | 83 | 84 | 86 | 84
Notes: Updated for October– Includes FU13 or all participants with closed windows (including study dropouts)

## Slide 5: Followup Retention by Site
Retention = Completed / (Enrolled – Dead) except FU 13 (windowed)
Chart: WFU
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 95 | 97 | 95 | 95 | 91 | 93 | 81
A-A | 92 | 97 | 90 | 90 | 89 | 89 | 81


Chart: Columbia
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 94 | 94 | 90 | 58 | 90 | 90 | 86
A-A | 88 | 88 | 84 | 50 | 82 | 84 | 81
Hisp. | 91 | 90 | 85 | 52 | 84 | 86 | 78
Chart: JHU
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 97 | 98 | 97 | 93 | 92 | 87 | 85
A-A | 91 | 93 | 92 | 86 | 88 | 79 | 78
Chart: Minnesota
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 91 | 97 | 98 | 95 | 94 | 91 | 93

Hisp. | 89 | 91 | 87 | 75 | 83 | 77 | 80
Chart: NWU
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 97 | 97 | 97 | 80 | 90 | 91 | 81
A-A | 95 | 94 | 92 | 68 | 82 | 86 | 76

Chin. | 96 | 97 | 98 | 86 | 95 | 93 | 91
Chart: UCLA
| FU 7 | FU8 | FU9 | FU10 | FU 11 | FU 12 | FU13
White | 98 | 99 | 99 | 97 | 91 | 88 | 87
A-A | 92 | 95 | 86 | 90 | 84 | 82 | 85
Hisp. | 89 | 89 | 88 | 84 | 81 | 72 | 75
Chin. | 93 | 93 | 91 | 81 | 78 | 82 | 80
Notes: Updated for October, 2013

## Slide 6: Follow-up 13 Productivity Closed Windows
Expected* Contacts Made
3: Wake Forest 769 639 83%
4: Columbia 776 667 86%
5: Johns Hopkins 691 657 95%
6: Minnesota 774 713 92%
7: Northwestern 841 739 88%
8: UCLA 903 807 89%
TOTAL 4754 4222 89%
* Study dropouts not included in these numbers
Notes: Updated for Oct, 2013

## Slide 7: Follow-up 13 Productivity
Site | Window Closed Interview Done | All Interviews Done | Additional interviews done and not included in retention slide | % of FU13 Completed
WFU | 639 | 652 | 13 | 74%
Col | 667 | 748 | 81 | 82%
JHU | 657 | 719 | 62 | 89%
Minn | 713 | 728 | 15 | 81%
NWU | 739 | 763 | 24 | 78%
UCLA | 807 | 905 | 98 | 86%
TOTAL | 4222 | 4515 | 293 | 82%
Notes: Updated for Oct. 2013

## Slide 8
 | Target Cumulative | Completed Cumulative | Percent of Goal
MESA Air – Recruited from MESA Family |  |  | 
Wake Forest | 44 | 44 | 100%
Columbia | 139 | 96 | 69%
Northwestern | 146 | 146 | 100%
UCLA | 16 | 16 | 100%
Minnesota | 80 | 58 | 73%
Johns Hopkins | 47 | 43 | 91%
MESA Air New Recruits |  |  | 
UCLA | 152 | 148 | 97%
Columbia | 95 | 83 | 87%
Follow-up 13 – Air/Family Participants
Notes: Updated for Oct. 2013

## Slide 9: Follow-up Retention
F/U 13
  Heterogeneity across sites improved
  MESA Air follow-up is on track for most sites  Those not finished by Oct 15 should be coded as not done.
F/U 14 has commenced
  Considerable heterogeneity across sites in startup and completion rates
  Includes medications inventory and residential history review
F/U 15 due to start January 2014
Notes: Updated for Oct, 2013

## Slide 10: Common Retention Obstacles
Declining cognitive function
Hearing loss
Aging, health issues, and life events require all available time and energy
Cultural and Immigration issues
Search options less effective with dropping of land lines
Insufficient number of contact people

## Slide 11: Approaches for 85%+ FU Retention
Revised Web Reports (for PIs and Coordinators) and Software Updates
Abbreviated FU call “Have you been hospitalized”
Letter/email asking the same (handwritten notes have been most effective)
Notes: Updated for Oct. 2013

## Slide 12: Follow-up 14
Call to discuss streamlining of electronic form
Issues with collection of medication data
Notes: Updated for Oct. 2013

## Slide 13: Newsletter
Last issue mailed in July
Current issue in near final draft – will mail in November
Reformatted for greater participant appeal:
  Full color
  More graphics and pictures
  More white space
  Articles contained on a single page if possible, no skipping pages to continue
Notes: Updated for Oct., 2013

## Slide 14: Participant Summary Report
Summarizes data from all five exams
November 1, 2013
Notes: New for Oct. 2013

## Slide 15: Ancillary Study Status
Study | Site(s) | Current Activities | Enrollment / participation
MESA Kidney | JHU | 6-7 hour clinic visit to collect blood at 6-7 time points. DEXA scan and arterial elasticity included. Blood samples are analyzed to measure the rate of iohexol clearing to determine a precise measure of kidney function. | ~375 participants (actual enrollment likely closer to 325)
MESA Air | Col. & UCLA | Mailed Health & Life Questionnaire. Data collection underway at Col. And will begin soon at UCLA. Participants receive gift card to Target or Starbucks upon completion. | MESA Air New Recruits only - ~250 expected
MESA Air / CCAR | WFU & UCLA (WFU complete, LA to commence Jan. 2014) | Home/Personal/Vehicle Air Quality Monitoring in each of two seasons via GPS tracking unit, proximity monitor, and self-reported time-location diary. | 50 participants at each site

## Slide 16: Ancillary Study Status (cont.)
Study | Site(s) | Current Activities | Enrollment / participation
MESA COPD | Col., JHU, NWU, UCLA | Follow-up to original COPD ancillary study. Recruitment to begin shortly. Procedures include clinical measures, blood draw, MR with gadolinium, spirometry, ECG, lung CT, questionnaires. | Total n=265, including 160 MESA Classic participants
MESA Lung Fibrosis | Col. only | Case/control study. Recruitment just completed. Selected participants had two exercise tests in the clinic to measure lung function. Lung fields from previous CT scans were | 83 participants enrolled

## Slide 17: Thank You!!!