## Main
# | Proposal Title | PI / Co Investigators | Status | Description | Proposed Dates | "Active" Status per Online Report | Produces Data | Target Final Data Transfer Date | Data Request Date | Complete Data Transfer Date | MESA Inv Release Date | Priority | Last Update | CC Contact (if not PI) | Comments | Released Data Set | Database location | Centers
A001 | Aortic calcium and coronary events in the multi-ethnic study of atherosclerosis | Criqui, Detrano, Wong, Allison, Kronmal, Shea, Liu, Carr, Saad, Folsom | Approved by NHLBI on 1/29/02. Grant submitted 2/1/02, funded 3/10/03. NHLBI approval on 9/14/04 to add lumbar bone density readings of abdominal scans and visceral and subcutaneous fat. Over 1980 baseline scans completed. Follow-up scans (Exam 4) have begun. | Cohort to receive aortic calcium determinations (abdominal CT scans) at exams 2 and/or 3, with follow-up at Exam 4, 9/05 - 6/07. Number of follow-up scans to be determined by available funding. | 3/10/03 - 2/28/07 | Yes | Yes | 2006-03-01 |  | 2006-03-01 | 2008-01-22 | 1 |  | Ronit |  | CT_Aortic_label | tRC_CT_Aortic tAS01_BoneMineralDensity | Harbor-UCLA, CC, and all FCs except JHU
A002 | A simple single-slice method for measurement of left and right ventricular enlargement by EBT | Budoff, Detrano | Study activity listed as 'Completed' per online report (2/5/08, DV) Revision approved by NHLBI 1/22/02. Initially active as pilot study. R01 application submitted 2/1/02, funded 8/1/03. 8,000 scans read to date (all first scans, and some follow-ups). Intra-reader and inter-scan variability evaluation completed. 70% of data analysis complete. 7 papers proposed, awaiting approval on 1. 12/14/05 - 1 paper published (academic radiology), two others submitted to P&P and approved. | no burden, involves only different protocol for reading of CT scans | 8/1/03 - 7/31/07 | Completed | Yes |  | 2006-03-30 | 2006-07-17 |  | 1 |  | Norma | Budoff 3/30: "As soon as we have the data completed, we can transfer the data to you. I am not concerned about exclusivity for publication. I can transfer an up to date file to you next month" | MESAe1AorticValvularCalcium | tAS2_AorticValvularCalcium | Harbor-UCLA, and all centers
A003 | Infections, lipid metabolism, and atherosclerosis | Nieto, Risby, Lima, Gaydos, Brando | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | JHU
A004 | Myocardial perfusion in the MESA cohort | Jerosch-Herold, Wilke, Jacobs, Folsom, Shahar | Study activity listed as 'Completed' per online report (2/5/08, DV) MB approved. Active (R01 HL65580) Data collection and MRI studies complete 10/03. 240 single and 22 reproducibility studies. NHLBI turned down request for no-cost extension. All remaining funds were returned and grant project was closed. 5 manuscripts: 1 in press, 2 under review, 1 to be revised, and 1 to be finalized. | partial Minnesota cohort, one MRI exam of myocardial perfusion with contrast injection within 1 year after baseline exam | 10/1/00 - 9/30/03 | Completed | Yes |  | 2006-06-28 | 2006-06-28 | 2007-01-11 | 1 |  | Johnson AND J-H; Craig | cd received w/ documentation | MRI_Ancllry_Perfsn_StPaul | tAS4_MRI_MyocardialPerfusion | Minnesota
A005 | Atherosclerosis and osteoporosis (old title - MESA bone (vitamin D-PTH and serum osteoprotegerin-linking bone density and coronary calcium)) (old title - Smoking, bone density, atherosclerotic calcification and the vitamin D - PTH axis (MESA Bone)) | Detrano, Lang, Cushman, Tracey, Kronmal, Anderson | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | Harbor-UCLA, and all centers
A006 | RR interval variability and atherosclerosis | Bigger, Shea | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | Columbia, and all centers
A007 | Regional left ventricular systolic and diastolic dysfunction by MRI myocardial tagging and precursors of global sub-clinical ventricular dysfunction, symptomatic heart failure, and cardiovascular death | Lima, Nieto, Bluemke, Boineau | MB approved. First of 2 submissions funded 9/01. MB approved to study additional 1,000 ppts. in Exam 2 at JHU and UCLA. SC approved extension into Exam 3 (250 ppts. each at JHU and UCLA) on 3/10/04. SC approved to study 2000 ppts. in Exam 4 on 8/11/04. Per 8/04, approx. 1,523 tagged MR studies performed, 1,184 analyzed by HARP. 525 new tagged MR studies done in Exam 2. R01 renewal of 2/1/05 funded | Study to gain insight into the progression of regional left ventricular dysfunction and its effect on development of symptoms of heart failure using Harmonic Phase Imaging (HARP). Will study 1/3 to 1/2 of cohort. 5 add'l min. of MRI magnet time plus add'l 30 min. to complete 3-D tagging w. gadolinium contrast. MRI follow-up in year 8. | 9/27/01 - 6/30/05 2nd phase: 7/1/05 - 6/30/08 | Yes | Yes | 2008-03-01 | data request 3/8/2006; reminder sent 8.7.06 |  |  | 1 |  | Robyn |  |  |  | Johns Hopkins, and all centers
A008 | Excess fatigue and subclinical cardiovascular disease | Fitzpatrick, Buchwald, Goldberg | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | U. Wash., and all centers
A009 | MESA family study | Rotter, Rich, Burke, Kronmal, Tracy, Detrano, O'Leary, Pankow, Liu, Post, Shea, Watson | ASC appr. 7/24/00, SC approved 8/00, NHLBI approved 9/00. Second submission dd. 11/1/02 funded 8/1/03. Training on 1/7/04. Recruitment started in a rolling fashion, from April thru June 2004. In Fall 2004 approval rec'd to make up recruitment goals by recruiting outside of MESA cohort. In winter 2004 approval to increase genetic testing to 150 genes/1536 polymorphisms and to add testing in 750 Caucasians. As of 12/31/05, 943 sibling visits (and 1819 sibpairs). MESA-Family Eye: 933 Completedphotography procedure, 883 participants photography scoring complete. | Genetic and phenotypic assessment of 1,800 siblings and 400 parents of 900 ppts. in MESA cohort and outside recruitment. Includes MESA Eye exam and MESA-Air questionnaire. | 8/1/03 - 6/30/08 | Yes | Yes |  | N/A | 1/12008 |  |  |  | Craig |  | MESAFam | Multiple database tables, see tFam_Cover as a starting point | All Centers
A010 | Secondary prevention in peripheral arterial disease | McDermott, Greenland, Cella, Hahn, Dolan | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | Columbia, Northwestern, UCLA, Minnesota, (others?)
A011 | MESA brain study | Shea, and PIs from 5 FCs (except U. Minn.), CC, Core Lab | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | All FCs (except UM) CC, Core Lab
A012 | Ability of a novel non-invasive screening test of skin cholesterol level to provide prognostic information on development of subclinical atherosclerosis or the progression of subclinical to clinical atherosclerosis (Skin Cholesterol Level) | Ouyang, (Szklo, Lima, Ding, Vaidya, Kronmal, Crouse) | Approved by NHLBI on 6/8/01 at JHU as a commercially funded pilot. Industry agreement Completed2/14/02. NHLBI approval on 2/12/03 to continue study into Exam 2. 941 unique subjects. Preliminary analyses completed. Paper submitted to "Atherosclerosis" accepted on 1/10/05. Measurements to be repeated at Exam 4 with support provided for coordinator time. No new status updates per 1/3/06. | Colorimetric measure of skin cholesterol uses digitonin peroxidase conjugate that binds to skin cholesterol. Colored product read with spectrophotometer. (If pilot project successful, may resubmit for full cohort and consider repeat measurement at follow-up visits.) Preliminary analyses completed. | 4/1/02 - 1/15/04 | Yes | Yes |  | data request 3/8/2006; reminder sent 8.7.06 | ??? |  | 1 |  | Sandi | Dataset already created, Norma to determine location and upload data into MESA database (2/5/08, DV) |  |  | JHU, CC
A013 | Factors associated with progression of carotid IMT in the MESA cohort | Polak, O'Leary, and PIs from all FCs, CC, and USRC | NHLBI approved 1/01. Grant funded on 6/15/03 (R01 HL69003). Exam 1-2: 176 pairs to be analyzed. Exam 3: 3,020 scans received, 475 pairs analyzed. Re-analysis taking place with change in methodology. Replicate analyses being performed to determine effect of cardiac cycle on IMT measurements. | Carotid Ultrasound B-mode studies to be performed on half of cohort at each of exams 2 and 3. Data currently being analyzed. | 1/1/03 - 1/1/08 | Yes | Yes | 2008-03-01 | contact emailed 3/8 (2007?) |  |  |  |  | Cam | 1 File expected consisting on Exam 2 and 3 data (combined) |  |  | All FCs, CC, and US RC
A014 | High resolution contrast MR for detection and characterization of carotid artery atherosclerosis | Wasserman, Bluemke, Lima, Nieto, Arai, Lai, Saad, Sinha, Gomes | Revised proposal appr. by NHLBI on 5/22/01. Funded 9/1/02. 441 ppts. recruited and 333 MRI studies done. 183 CCAs and 131 ICA/plaques analyzed to date. Database program managed by Dr. Lai. Grant in 1 yr no-cost extension for completion of the analysis This grant is currently in a 1 year no cost extension for completion of analysis as per 12/17/05. May acquire a few additional MRI exams for exam reproducibility, which was approved by MESA. | Group A and B: Hi-Res contrast MR with injection of gadolinium by IV catheter. | 10/1/02 - 8/31/06 | Yes | Yes | 2008-03-01 | 2006-03-08 | pending additional cases (see "comments") |  | 1 |  | Norma | Wasserman 3/8/06: We have been working on matching our numbers with those of the CC to ensure all data is accounted for. Furthermore, a follow-up component of the study just finished a few months ago and we have additional cases to analyze. We will work on getting this done over the next few months and then plan to send the data to the CC.: |  |  | Hopkins and UCLA
A015 | Ethnic and gender differences in the relationship between bone mineral density and coronary calcification | Detrano, Schreiner, Kronmal, Cushman | Per online report, study active status listed as 'Unfunded' (2/5/08, DV) |  |  | Unfunded | No | - | - | - | - | [6 empty] | All FCs, CC, CTRC
A016 | Plasma sphyngomyelin as an atherogenic risk factor | Tall, Jiang, Tabas, Shea, Tracy | Study activity listed as 'Completed' per online report (2/5/08, DV) NHLBI appr. 5/19/01. Study funded as part of SCOR grant (HL56984). 6,373 samples measured, biochemical analyses complete, working on data analyses with Dr. Shea. All measurements and analyses completed, one paper being written. | 40 microl of plasma to measure plasma sphingomyelin as an atherogenic risk factor. | 1/1/03 - 12/31/03 | Completed | Yes |  |  | 2006-04-27 |  | 1 | 2006-04-27 | Craig | Data received: Original excel data (as sent from Elaine at the lab): n=6747 2. Jen's de-duplicated SPSS file: n=6746 3. SM data merged/matched with MESA ID's and some Exam 1 data from the coordinating center: n=6708 | MESAe1Sphyng | tAS16_Sphyngomyelin | Columbia, Blood Lab, CC
A017 | Retinal microvascular characteristics as predictors of subclinical and clinical cardiovascular diseases (MESA-EYE) | R. Klein, Wong, Burke, B. Klein, Hubbard, Shea, Siscovick | ASC appr. 4/19/01, SC appr. 5/2/01, NHLBI appr. 5/21/01. Funded 6/1/02. Photographers certified. As of July 2004, photos received = 12,257 Preliminary grading = 12,257. Final grading = 12,352 (95 ppts only had one eye photographed). 7052 eyes RA graded, including 420 QC photos. Paper proposal AC-016, AC-039, and AC-042 approved. Papers for AC-016 and AC-039 submitted to journal. | Exam 2, retinal photography following dilation in dark room for 5 min. | 4/1/02 - 3/31/06 | Yes | Yes | 2004-01-31 |  | 2004-05-10 |  | 1 |  | Sandi | 3 Files expected: 1) Retinal Reflection 2) Refraction 3) EyeQ See study A027 for overlap |  | tRC_Eye_Final | All FCs, CC
A018 | Utilization of completmentary and alternative medicine (CAM) substances and practices in the MESA cohort | Jackson, Burke, Fitzpatrick, Standish | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | All FCs, CC
A019 | Subclinical coronary arteriosclerosis with MRI | Hundley, Goff, Burke, Carr, Link, Morgan, Hamilton | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | WFU
A020 | MESA-Gums | Hujoel, Shea, Spiekerman, Drangsholt, Papapanou, etc. | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | All centers
A021 | Normative values for the adult right ventricle by MRI | Bluemke, Tandri, Lima, Rutberg, Calkins | Study activity listed as 'Completed' per online report (2/5/08, DV) SC approved 11/7/01. NHLBI approved. Reading of MRIs for size of right ventricle completed. | No burden. Involves only measurement of right ventricle on existing MESA MRIs to establish normative values | 1/1/02 - 12/31/03 | Completed | Yes |  | data request 3/8/2006 | ??? |  | 1 |  | Norma | Norma to ask Linda about data (2/7/08, DV) |  |  | JH Hosp. (data from all centers)
A022 | Measurement of normal thoracic aortic wall thickness by MRI imaging | Li, Kamel, Anderson, Lima, Bluemke, Kumbasar | Study activity listed as 'Completed' per online report (2/5/08, DV) SC approved 11/7/01. NHLBI approved. Data collection complete. One publication in March 2004. | No burden. Involves only measurement of Aortic wall thickness on existing MESA MRIs to compare data with Framingham risk factors and correlate data with US measures of intimal media thickness. | 11/8/01 - 12/31/03 | Completed | Yes |  | 2006-03-14 | ??? |  | 1 |  | Bluemke; Norma | Dataset likely completed, to be located (2/5/2008, DV) Files sent. Eric Johnson drafting a data dictionary. |  |  | JH Hosp.
A023 | Neighborhoods and CVD in a multi-ethnic cohort | Diez-Roux, Brown, Morenoff, Shea, Evenson, O'Meara, Rodriguez | SC approved 12/19/01. NHLBI approved. NIH grant funded 6/1/03. Data collection began 4/03 - 6,181 ppts. to date. Additional funding from RWJF (12/04-11/07) for new analyses on neighborhoods and self-reported physical activity (Evenson, PI). | Questionnaire (exams 2 & 3) to characterize neighborhood environments and participants' exposure to them | 4/1/03 - 3/30//07 | Yes | Yes | 2005-09-15 |  |  |  | 1 |  | Ellen | CHECK FOR POSSIBLE GEO IDENTIFIERS (2/5/2008, DV) |  |  | All FCs, CC
A024 | Long-term exposure to ambient particulate matter and subclinical atherosclerosis | Diez-Roux, Barr, Keeler, Samson, O'Meara | SC approved 12/19/01. NHLBI approved. EPA grant submitted 1/18/02 funded. Data collection complete: 6,194 ppts. total | Questionnaire (exams 2 & 3) to obtain residential history information and infer exposure to air particles | 4/1/03 - 3/30/07 | Yes | Yes | 2005-09-15 |  | 3/2/0/2006 |  | 1 |  | Ellen | CHECK FOR POSSIBLE GEO IDENTIFIERS (2/5/2008, DV) | None - identifying | tAS24_ParticipantLocation | All FCs, CC
A025 | Validation of PC-based coronary scoring software by comparison with MESA scoring software | Detrano, Wong | Study activity listed as 'Completed' per online report (2/5/08, DV) SC approved 1/16/02, NHLBI approved. Project funded commercially. Image Analysis unable to deliver operational software. 300 random scans read using the MESA software and that of Rephot Imaging N19, read twice, CC did analysis. Completedstudy. | 300 random scans , read twice for QC, to be re-read by a second reader using Image Analysis Software. Comparison of median scores between this and MESA software. Funding from Image Analysis. | 2003-01-31 | Completed | See Comments | 2004-11-01 |  | 2005-03-30 |  | 1 |  | Craig | Data complete and paper written, Craig to locate data and post online. Per Craig, data produced for QC purposes only (2/5/2008, DV) | None-specific QC validation activity | tRC_CT_S oftwareTest_Adjusted | CT Reading Ctr.
A026 | Blood pressure measurement: device variability of the Dinamap Pro 100 | Shea, Rabinowitz | Study activity listed as 'Completed' per online report (2/5/08, DV) SC approved 1/16/02, NHLBI approved 1/31/02. Local funding. Data collection complete, analyses performed. Paper published in Am. J. Epi. | 30 paired BP measurements in each of 30 ppts. using three Dinamap Pro 100 devices. | 3/1/02 - 6/30/02 | Completed | Yes |  | data request 3/8/2006 | 2006-03-13 |  | 1 |  | Craig | Craig to locate sent data and post online (2/7/08, DV) Data files sent to Craig from Shea 3/13/06 |  |  | Columbia
A027 | Visual impairment and refractive error in a multi-ethnic U.S. population (MESA-Vision) | Wong, R. Klein, Burke, B. Klein, M. F. Cotch | SC approved 2/27/02. NEI intramural R&D funding. Completedvision and refraction exams in Exam 2. Vision Completion Forms rec'd = 6,171. Number with complete refraction = 6,043. Paper proposals AC 015 and AC 025 submitted and approved. | Auto-refractor uses infra red rays to measure refractive power of ppts' eyes.(Exam to coincide with MESA-Eye retinal photography, study A17) | 6/1/02 - 5/31/06 | Yes | Yes | 2004-01-31 |  |  |  | 1 |  | Sandi | 3 Files expected: 1) Retinal Reflection 2) Refraction 3) EyeQ See study A017 for overlap |  |  | All FCs, CC
A028 | Statistical methods and analysis for arterial pulse wave data in MESA | Polak, Lumley, Kronmal, Nelson, Yanez, Katz, Brumback, Post | Study activity listed as 'No' per online report (2/5/08, DV) SC approved 4/10/02. Grant submited 6/18/02 not funded. Resubmission is delayed due to need for more preliminary data on feasibility. | No burden. Involves use of existing pulse wave data to apply new statistical methods of analyzing this data and applying it to the MESA cohort | 4/1/03 - 12/31/06 | No | Yes |  | contact emailed 3/8 (2007?) | 2007-09-01 | 2007-11-01 | 1 |  | Lyn |  | MESAe1PulseWaveSEMOR | None - dataset prepared form processing of original large raw pulse wave datafiles | CC
A029 | Socioeconomic factors, stress, and inflammation in a multi-ethnic cohort | Diez-Roux, Shea, Seeman, Cushman | SC approved 8/8/02, NHLBI approved 8/26/02, submitted as R01 on 6/1/03, funded 5/1/04, 743 ppts. enrolled to date. SC approved data collection into exam 4 8/26/05. | 1,000 ppts. collect 6 saliva samples/day over 3 days, plus 12 hr. urine sample. Subset of 50 will provide additional 24 hr. urine sample. Data collection into exam 4 | 1/1/04 - 7/1/05 | Yes | Yes |  |  | 2007-10-30 | 2007-10-30 |  |  | Sandi |  | MesaStress | Multiple database tables | Columbia, LA, CC, Lab
A030 | Sex hormone levels and subclinical atherosclerosis | Ouyang, Gapstur, Szklo, Dobbs, Golden, Liu, Kopp, Heckbert | NHLBI approved 9/19/02. Linked R01 Grant submitted 10/1/02, funded on 7/1/03. Control blood samples obtained. Samples sent to U. Mass for assays, of which 3161 for women and 2898 for men performed to date. QC assays performed in 224 samples. No new status updates per 1/4/06. | .5 ml of stored blood to be assayed for endogenous sex hormones to evaluate potential association with CHD risk. Samples to be assayed at U. Mass, Dr. Longcope's lab. | 7/1/03 - 6/30/07 | Yes | Yes | Ongoing | data request 3/8/2006; reminder sent 8.7.06 | 2007-04-27 |  | 1 |  | Sandi |  |  | tAS30_SexHormone | JHU, Northwestern, CC, Blood Lab
A031 | Inflammation and subclinical cardiovascular disease in rheumatoid arthritis | Bathon, Post, Lima, Zeger, Szklo, Detrano, O'Leary, Tracy | NHLBI approved 9/17/02, receivedd Shannon award for planning. R01 funded 5/1/04. | Proposal to examine the role of imflammation on CVD in patients with rheumatoid arthritis (RA). 200 RA ppts. will undergo MESA protocol and be compared with JHU MESA ppts. (as controls). | 5/1/04 - 4/30/09 | Yes | No | - | - | 2007-08-07 | - |  |  | Norma |  |  |  | JHU, CC, all RCs, Blood Lab
A032 | Left ventricle filling and ejection rates in MESA | Tekes, Szarf, Lima, Bluemke | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | MR Reading Center
A033 | Sleep disordered breathing and subclinical CVD (MESA Sleep) | Shahar, Redline, 6 FC investigators, Kronmal | Per online report, study active status listed as 'Unfunded' (2/5/08, DV) |  |  | Unfunded | No | - | - | - | - | [6 empty] | All FCs, CC
A035 | Aortic wall thickness in MESA | Bluemke, Lima, Lai, Natori | SC approved 5/9/03, MB approved 5/13/03. Internal funding at JHU. 600 measurements per 7/26/04. No change in status per 8/05. | Aortic wall thickness measurements perpendicular to the vessel lumen on all ppts. with cardiac MR in Exam 1 | 5/15/03 - ? | Yes | Yes |  | data request 3/8/2006 | 2008-02-05 | 2008-01-09 | 1 |  | Norma | Norma to inquire of data status (2/7/2008, DV) | MESAe1as35_AorticWall | tAS35_MRIAorticWallThickness | JHU
A036 | Novel markers of inflammation and immunity | Jenny, Tracy, Kuller, Fried, Psaty, Kronmal, Walston | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | - | - | - | - | [6 empty] | Vermont
A037 | Novel markers of inflammation and atherosclerosis | Jenny, Tracy, Kuller, Psaty, Kronmal | SC approved 5/30/03, grant to AHA on 7/14/03, approved for funding. SAP and PTX3 assays will be done 1/06. | 1,000 baseline blood samples will be evaluated for cross sectional associations with two novel inflammatory markers, SAP and PTX3, and CRP | 1/1/04 - 12/31/07 | Yes | Yes |  | data request 3/8/2006 | 2006-04-05 | 2007-02-21 | 1 |  | Norma | SAP data. Pending: pentraxin 3 data; data dictionary | MESA_AS37_SAP_PTX3 | tAS37_saP_Pentraxin3 | Vermont
A038 | Use of herbal medicine, botanicals, and dietary supplements in MESA | Fitzpatrick, Jackson, Standish | SC approved 5/30/03, grant submitted to NCCAM on 8/15/03. Funded 6/1/04. Data coding in progress to date. Abstract prepared for submission of first paper. No status updates per 12/05. | Secondary data analyses on baseline data from the MESA Medications and Diet Assessment forms on CAM use in different minority groups. | 4/1/04 - 3/31/06 | Yes | No | - | - | - | - |  |  | Annette |  |  |  | UW
A039 | Prospective study of air pollution and atherosclerosis (MESA Air Pollution) | Kaufman, Siscovick, Diez Roux, MESA PIs, Barr, Kinney Astor, Shahar, Jacobs, Sheppard, Lumley, Larson, Liu, Sampson, Cohen | approved by SC on 6/11/03. EPA Grant application submitted on 7/23/03; Funding began in August 2004. IRB revisions approved in Oct/Nov 2005, staffing at Field Centers complete, MESA Air subject recruitment began 3/05, air sampling began 7/05. Revisions to protocols approved 12/19/05. | 10-year study to determine the long-term effects of exposure to air pollution on atherosclerosis. In addition to MESA exam components, MESA ppts. fill in a home characteristics questionnaire (25 min) Completedat clinic. MESA Family siblings and MESA-Air new recruits will complete additional MESA baseline questionnaires. Up to 900 subjects involved in home air pollution monitoring. Brief questionnaire for ppts. doing indoor monitoring, diary for ppts. doing personal monitoring. | 9/1/04 - 7/31/14 | Yes | Yes | Exam 4 7/2008 All 1/1/2009 | [5 empty] | Karen |  |  | <<multiple files>> | All FCs, CC, Lab, CT, US
A040 | Endothelial dysfunction, biomarkers and lung function (MESA-Lung) | Barr, Carr, Detrano, Enright, Hoffman, Jiang, Kronmal, Liu, Polak, Kawut, Watson, Shahar, Shea, Smith, Tracy, Szklo, Hankinson, Punjabi, Wong, Wang | SC approved 8/13/03, NHLBI approved 9/12/03. Grant funded 7/1/04. Data collection started 10/04. Revision to add JHU ppts. and MIP measurements approved 9/04. Revision to add 300 MESA-Air new recruits and 180 MESA Family new recruits at Columbia approved 7/05. 12/18/05 - Receiving CTs scans images and are reading them for lung density as previously approved. Main study is progressing well (n=1742 so far).“Validation study” at WFU and Columbia is Completed(n=43).“Family pilot” at Columbia has started (n=50 so far). “Air New Recruits” study is pending the start of new recruitment by MESA-Air (1/1/06). 1 abstract submission to the ATS meeting | Spirometry questionnaire, measures, and maximal inspiratory pressure (MIP) on 3,800 ppts., in Exams 3 and 4; cotinine levels of Exam 1 urine on 3,800 ppts.; ICAM and E-selectin anal. on approx. 250 and 1,125 Exam 1 blood samples, respectively; Genotyping of sICAM-1, E-selectin, and eNOS genes (20-30 SNPs) on 1,625 ppts. CT validation study of 25 ppts. ea. at WFU and Columbia involving additional chest CT. (Also, spirometry questionnaire, measures and MIP on 300 new MESA-Air recruits (Columbia and UCLA) and up to 180 MESA-Family ppts. (pilot at Columbia only)). | 8/2/04 - 8/1/08 | Yes | Yes | Spirometry done LungQ 8/2008 LungCT 7/2008 |  | 2007-09-11 | Spirometry 11/1/2007 |  |  | Karen |  | MESALung_Cotinine_11-14-2007 MESALung_Spirometry_9-17-2007 MESACG_SERPINA1_ByIDNO_09302007 | <<multiple files>> | All FCs, CC, Lab, CT
A041 | Fat redistribution and metabolic change in HIV infection: Protocol 2 | Grunfeld, Kronmal, Tien, Bacchetti, Scherzer, Shlipak, O'Leary, Polak, Heymsfield, Johnson. | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | No | - | - | - | - | [6 empty] | CC
A042 | Epidemiology of vascular inflammation and atherosclerosis | Tracy, Jenny, Bouchard, Kronmal, Psaty, Huber | ASC approved 9/10/03, SC approved 9/17, NHLBI approved 9/25/03. Grant submitted 10/1/03 funded 7/1/04. Sample collection planned to start 10/05 in Exam 4. Per 1/10/06, 180 blood samples drawn at Exam 4 visit have been rec'd. These blood samples have been processed for cell-based measurements. Plasma from samples has been inventoried and stored at – 80 C for further assay work as described in AS. | Study to determine differences in cellular function that define different disease rates in individuals. Focus on lymphocytes (T cell subsets, T cell differentiation potential), monocytes activation and Tissue Factor expression, and circulating endothelial cells and endothelial progenitor cells. | 7/1/04 - 6/30/09 | Yes | Yes | 8/2008 | [5 empty] | Sandi |  |  |  | All FCs, Lab, CC
A043 | A genetic variant in CORIN, the pro-natriuretic peptide converting enzyme, is associated with left ventricular hypertrophy in African Americans with hypertension | Dries, Rame, Post, Lima | SC approved 9/17/03. DNA sharing agreement. NHLBI approved 11/12/03. Lab samples received and assays performed. Paper proposals approved, submitted, and first manuscript accepted in Circulation 8/05. No new status updates per 1/9/06. | Study to determine the role of two loci in the Corin gene on cardiac hypertrophy-sensitizing mutation in African Americans with hypertension. Testing to be performed on all ppts. who consented to genetic testing. | 12/1/03 to 12/1/07 | Yes | Yes |  | 2006-03-08 | 2007-05-02 |  | 1 |  | Rame Craig |  |  | tAS43_Corin | Lab, CC
A044 | Statistical issues in imaging methods to detect CVD | Yanez, Wang, Nelson, Polak, Kronmal, Detrano, | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | No | - | - | - | - | [6 empty] | CT and US RCs, CC
A045 | Serum osteoprotegerin levels and coronary calcium | Shin, Detrano, Romero, Jenny, Johnson | ASC approved 11/5/03. SC approved 11/20/03. EVEREST Fellowship grant funded. Assays on 400 samples performed. Preliminary data analyzed. Abstract submitted to AHA to be presented 11/13/2005. | Exam 1 serum to be analyzed at MESA Lab. Study to evaluate the relationship between OPG with prevalence and extent of coronary calcium. | 7/1/04 - 6/30/05 | Yes | Yes | 2005-06-10 |  | 2008-02-06 |  | 1 |  | Craig |  |  | tAS45_Osteoprotegerin | Lab, CC, CT RC
A046 | Coronary artery wall thickness in MESA | Bluemke, Stuber, Lima, Lai, Liu | ASC approved 1/7/04, SC approved 1/14/04, OSMB approved 1/28/04. Grant submitted 2/1/04 not funded. Resubmitted on 11/1/04, funded 8/05. | 300 ppts. at JHU will be recruited for an MR exam, overlapping with Exams 3 & 4. Two years after initial exam, 80 of these ppts. will return for a second MR . | 12/1/04 - 8/31/07 | Yes | Yes | 8/2008 |  | ??? |  |  |  | Norma |  |  |  | JHU, MR-RC, Northwestern FC
A047 | Association of serum markers of secondary hyperparathyroidism with coronary artery calcification in a multi-ethnic study of persons with mild-moderate renal insufficiency: MESA | Kestenbaum, Seliger, Siscovick, Detrano, Kronmal | Study activity listed as 'Completed' per online report (2/5/08, DV) ASC approved, 1/28/04, Lab approved 3/10/04, SC approved 3/10/04, NHLBI approval 3/31/04, OSMB approved 6/17/04. Funding for assays available from K23 grant. Received PTH measurements on 211 ppts., awaiting remaining analytes from lab. Prelim. analysis begun. Amendment to expand the cohort from participants with abnormal creatinine (about 180 participants) to those with an estimated glomerular filtration rate less than 60. SC approved 10/6/05. NHLBI approved 10/10/05. 12/15/05 - Received data for about 180 of the 530 expected measurements. Measurements for outstanding participants ongoing and expected by 2/06-3/06. | Baseline serum from 211 ppts. with mild-moderate renal insufficiency to be evaluated for phosphate, parathyroid hormone, 25 hydroxy vit. D, and 1,25 dihydroxy vit. D to determine association with presence of coronary artery calcification | 4/1/04 - ?? | Completed | Yes | 3/15/2008 |  | ??? |  |  |  | Craig | Craig to follow-up with De Boar (2/7/2008, DV) |  |  | Blood Lab, CT RC, CC
A048 | Depression, cognitive decline and cardiovascular disease: epidemiology and mechanisms | Lyketsos, Lee, Fitzpatrick, Szklo, Burke, Shea, Liu, Kronmal | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | No | - | - | - | - | [6 empty] | CC, All FCs (except U. Minn.)
A049 | Papillary muscle mass in the left ventricle | Bluemke, Claussen, Lima, MR Committee | Study activity listed as 'Completed' per online report (2/5/08, DV) ASC approved 4/7/04, SC approved 4/14/04, local funding at JHU. Abstract submitted to Radiologic Soc. of North Am. Oct. 2004. Paper submitted to journal. | Study to measure the normal relationship between left ventricle mass and papillary muscles. | 5/1/04 - ?? | Completed | Yes |  | data request 3/8/2006 | 2007-04-23 |  | 1 |  | Norma |  |  | tAS49_MRIPapillaryMuscleMass | MR Reading Center, JHU
A050 | SEA (a.k.a. PDAY/MESA) Genome-wide association study to measure the association between common SNPs in the human genome and extent of aortic and coronary atherosclerosis among subjects in the PDAY cohort | Herrington, Rich, Howard, Lange, Mychaleckyj, Strong, Malcom, Boudreau, Fallon, Hixson, Rotter, Kronmal, Arnett | ASC approved 4/28/04, SC approved 5/12/04, NHLBI approved 5/12/04. Second grant submission on 3/1/05, rec'd score of 153 (11th percentile), funding likely. Per 1/5/06, grant approved at Council, but have not received award stmt pending Congressional approval of new NIH budget. | Two-stage genome-wide association study to identify single nucleotide polymorphisms associated with sub-clinical atherosclerosis. PDAY subjects will be "discovery" cohort and MESA subjects will be validation cohort. Also to test gene-gene and gene environment interactions and association with other atherosclerosis phenotypes. | 12/1/05- 11/30/10 | Yes | Yes | 7/2009 | [5 empty] | Craig |  |  |  | Lab, CC
A051 | Role of family history in CAD risk assessment | Scheuner, Blumenthal, Garber, Setodji | ASC approved 7/28/04, SC approved 8/11/04. NHLBI approved 8/19/04. PI has own funding thru 6/30/05. Subcontract to UCLA Ctr. for Health Policy Research. (2/1/05-9/30/05)from Ogilvy PR Worldwide, contractor for CDC, to evaluate validity of familial algorithms created for the CDC family history tool using available population-based data. IRB approval rec'd. Data rec'd 6/28/05. Prelim. analyses Completedat UCLA describing prevalence of familial risk levels and associations between familial risk and CHD. Modified proposal, which included gaining access to results of ABI and IMT in addition to CAC. SC approved mod. 10/17/05, NHLBI approved 10/18/05. R21 NHLBI grant resubmitted on 11/1/05. | Study to evaluate clinical validity and utility of algorithms for interpretation of familial CAD risk. Will use MESA family Hx data, demographic info, lab results, and subclinical markers of atherosclerosis (I.e., CAC scores, ABI and IMT). | 07/01/06 - 06/30/08 | Yes | No | - | - | - | - |  |  | Craig |  |  |  | CC
A052 | Association of the human KLOTHO gene with coronary artery calcium, carotid intimal media thickness, and ankle-brachial index in the MESA cohort | Arking, Kao, Post, Chakravarti, Dietz | ASC approved 8/4/04, SC approved 8/11/04. NHLBI approved 8/19/04, PI has own funding. Samples were requested on 12/22/05. | Study to evaluate the association of the human KLOTHO gene variants and CAD, stroke and mortality. | 9/1/04 - 8/31/06 | Yes | Yes | ??? | [5 empty] | Craig | Craig to inquire about data (2/7/2008, DV) |  |  | Lab, CC, JHU
A053 | Multi-ethnic study of autoimmunity and atherosclerosis | Majka, Liu, Chang | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | 8/14/2008 | [5 empty] | Craig |  |  |  | Lab, CC, NU
A054 | Atherosclerosis risk refinement - a multimarker approach using microarrays (old title - Gene expression profiling of peripheral blood leukocytes in MESA participants) | Huang, Lloyd-Jones, Liu, Rajamannan, Lin | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | 8/14/2008 | [5 empty] | Craig |  |  |  | All 6 FC
A055 | Osteoprotegerin: The missing link between atherosclerosis and osteoporosis? | Shin, Detrano, Criqui, Jenny, Lang, Johnson, Papas, Romero | ASC & Lab approved 9/8/04, SC & NHLBI approved 9/14/04 (Study replaces A15). No change in status per 7/20/05. | Osteoprotegerin assays of existing Exam 2 serum from 803 ppts. with coronary and abdominal aorta scans, to determine the relationship between BMD and CAC, and between osteoprotegerin and BMD and CAC. | 7/1/05- 6/30/07 | Yes | Yes | 2/2/2006 |  | 2006-02-02 |  | 1 |  | Craig |  |  | tAS55_BoneMineralDensity | CTRC, Lab, CC
A056 | Automatic vessel wall contour detections and quantification of wall thickness in in-vivo MR images of the human aorta | Adame-Valero, Lima, van der Geest, Lelieveldt, Reiber | Per online report, study active status listed as 'Complete' (2/5/08, DV) |  |  | Completed | Yes |  |  | ??? |  |  |  | Norma | Norma to inquire if data generated (2/7/2008, DV) |  |  | MR RC, JHU
A057 | Cystatin-C - A novel measure of renal function and cardiovascular risk | Shlipak, Siscovick, Katz, Kramer, Sarnak, Stehman-Breen, Cushman, Jenny, Burke, Criqui, Lima, Jacobs, Shea | ASC approved 3/2/05, NHLBI approved 3/22/05. Dade-Bering to donate reagents. Measurements have been made in approximately 2/3 of the sample. | Study to measure Cystatin-C as a novel biomarker of renal function and its association with chronic heart failure and cardiovascular mortality risk, as well as inflammatory markers and procoagulant biomarkers. |  | Yes | Yes | Ongoing |  | 2007-08-13 | 2007-08-15 |  |  | Ronit |  | MESA_as57_cystatinC | tAS57_CystatinC | All FCs, CC, Lab
A058 | Subclinical atherosclerosis in lupus patients and MESA controls in Baltimore | Petri, Post, Kiani, Szklo, Astor, Bathon | ASC approved 2/10/05, NHLBI approved 3/4/05. | Comparison of CAC and carotid IMT in ppts. of the Lupus Atherosclerosis Prevention Study (LAPS) with 20 scans from matched MESA controls. Requires access to 20 helical CTs and 20 carotid US images for rereading and reproducibility with LAPS analytic software. |  | Yes | No | - | [5 empty] | Norma |  |  |  | JHU
A059 | Pericardial fat and subclinical and clinical meaures of coronary heart disease in a multi-ethnic sample of US adults | Ding, Carr, Krittchevsky, Burke, Leng, Criqui, Detrano, Szklo | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes |  |  | 2007-07-10 | 2007-08-27 |  |  | Craig |  | MESAe1PericardialFat07132007 | tAS59_PericardialFat | WFU, CT RC, JHU
A060 | Assessment of adipose tissue distribution in the abdominal cavity, abdominal wall and thigh: Proposal for Multi-Ethnic Study of Atherosclerosis | Harris, Criqui, Carr, Allison, Visser, Lang | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | [10 empty] | All FCs except JHU, CC
A061 | Myocardial infarction and cardiovascular disease risk factors among HIV-infected patients in comparison to HIV un-infected individuals | Crane, Saag, Biggs, Kitahata | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | No | [10 empty] | CC
A062 | Diet, biomarkers, and lung function | Jiang, Barr, Shea, Jacobs, Jenny | Study activity listed as 'No' per online report (2/5/08, DV) SC approved 9/29/05, NHLBI approved 8/31/05. K-award application submitted 10/1/05. | Study to evaluate diet on COPD. Spirometry and dietary intake data from MESA Lung ppts. plus new measures of biomarkers (nitrotyrosine, 25-hydroxy Vitamin D) to determine effect of novel dietary factors on lung function. Also, CTs from all exams to be re-read for lung density. | 7/1/06 - | No | Yes | Ongoing | [5 empty] | Karen |  |  |  | Lab
A063 | Assessment of coronary artery calcification in patients with primary hyperparathyroidism – a pilot study | Streeten, Mitchell, Hines, Post | Per online report, study active status listed as 'Completed' (2/5/08, DV) |  |  | Completed | No | [10 empty] | Local
A064 | The association of hemoglobin with cardiac structure and function and subclinical atherosclerosis in a multi-ethnic cohort. | Astor, Bluemke, Lima, Kramer, Jacobs, Burke, | Study activity listed as 'Withdrawn' per online report (2/5/08, DV) SC approved 11/7/05. NHLBI approved 11/9/05. PI is planning implementation | Whole blood for hemoglobin measurement. |  | Withdrawn | No | Ongoing | N/A |  |  |  |  | Norma |  |  |  | JHU, WFU
A065 | The relationship of aging, central fat, and muscle to inflammation and subclinical and clinical cardiovascular disease (CVD). | Criqui, Allison, Cushman, Carr, McClelland, Lang | ASC approved 8/31/05. SC approved 9/1/05, NHLBI approved 9/6/05. | Proposal is to read CT scans for various measures of abdominal fat and correlate with risk factors and subclical CVD. |  | Yes | Yes | Ongoing | [5 empty] | Robyn |  |  |  | All FCs, except JHU
A066 | Telomere length, stress, and subclinical cardiovascular disease | Diez-Roux, Shea, Cushman, Jenny, Seeman | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes |  |  | 2008-01-16 | 2008-01-16 |  |  | Sandi |  | MESA Stress - Telomere Length | tAS66_Telomere
A067 | Predictors of right ventricular function in the multi-ethnic study of atherosclerosis (MESA-RV) | Kawut, Barr, Bluemke, Kronmal, Lima, Tracy | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | Ongoing | [5 empty] | Craig |  |  | tAS67_RV_MRI | CC, Core Lab, JHU
A068 | The African American-Diabetes Heart Study (AA-DHS) | Freedman, Carr, Bertoni, Rich | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | [6 empty] | Craig |  |  |  | none
A069 | Cardiac Mapping Project. | Young, Finn,Toga, Bluemke | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | No | [10 empty] | UCLA, JHU, CC
A070 | Oxidative Stress Genes and Atherosclerotic Complications of Hypertension. | Klos, Arnett, Peyser | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | ??? | [7 empty] | "Produces Data" field left blank per Craig (2/8/2008, DV) |  |  | Lab
A071 | Effect of Chronic Inflammation on Atherosclerosis Outcomes in Rheumatoid Arthritis. | del Rincón, Arya, Duggirala, Escalante, Jenkinson, Polak, O'Leary | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | ??? | [7 empty] | MESA component not yet active (2/8/2008, DV) |  |  | Lab
A072 | Body Composition and Rheumatoid Arthritis | Bathon, Blumenthal, Szklo, Criqui, Detrano, Polak | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | [10 empty] | JHU, CC, al RCs, Blood Lab
A073 | Pilot study to measure endothelial progenitor cells in MN | Folsom, Taylor | Per online report, study active status listed as 'Withdrawn' (2/5/08, DV) |  |  | Withdrawn | No | [10 empty] | Minnesota
A074 | Sleep-Disordered Breathing and Risk Factors for Cardiovascular Diseases in Whites and Hispanics in U.S. and Japanese in Japan | Tanigawa, Folsom, Iso, Ohira. | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | 1/1/2009 | [5 empty] | Craig |  |  |  | MN
A075 | Altered mineral metabolism – associations with urine albumin excretion, inflammation, and coronary artery calcification. | de Boer, Kestenbaum, Siscovick | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes |  |  | 2007-12-19 | 2007-12-19 |  |  | Craig |  | MESAa75MinMetabl MESAa75e1Season | tAS75_MinMetab | Lab
A076 | Left and Right Atrial Volumes in Cardiovascular and Pulmonary Disease in MESA | Daniel, Carr, Hundley, Barr, Ambrosius | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No. | Study Not Active Yet | [10 empty] | CC; WFU (analysis)
A077 | Fetuin-A – A Novel Inhibitor of Dystrophic Calcification and Promoter of Insulin Resistance | Ix, Siscovick (Sponsor), Shlipak, Katz, Jenny, Criqui. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | Lab
A078 | Occupation Coding in the Multi-Ethnic Study of Atherosclerosis (MESA) | Barr, Diez-Roux, Stukovsky, Kaufman, Kronmal | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | 1/1/2009 | [5 empty] | Karen |  |  |  | All Centers
A079 | Association of Brain Natriuretic Peptide and Troponin T with Global and Regional Left Ventricular Dysfunction and Incident Heart Failure . | LIma, Bahrami, Daniels, Maisel, Tracy, Siscovick, Greenland, Cushman, Criqui | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet
A080 | Spatial investigation of sources, composition, and chronic health effects of coarse particulate matter (PM10-2.5) in the Multi-Ethnic Study of Atherosclerosis Air Pollution study (MESA Air) cohort | Adar, Larson, Kaufman, Sheppard, Sampson, Simpson, Cohen, Barr, Daviglus, Burke, Jacobs. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | UW, CC, NU, WFU, MN
A081 | Apolipoproteins B and A-1 in relation to atherosclerosis, obesity, and race in a multiethnic population | Paramsothy, Heckbert, Knopp, Marcovina, Tsai M, Bertoni. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | CC
A082 | Associations of Lipoprotein-Associated Phospholipase A2 Mass and Activity with Subclinical Cardiovascular Disease in the Multi-Ethnic Study of Atherosclerosis. | Cushman, Jenny, Rosenson, Greenland, Criqui, Siscovick | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | Lab, CC
A083 | Assessing the validity and utility of multiplex genetic susceptibility testing for CHD | Scheuner, Keeler, Setodji, Rotter, Taylor, Guo, Blumenthal | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | CC, lab
A084 | A Multi-Ethnic Study of Subclinical Renal Artery Atherosclerosis, Kidney Function and Incident Cardiovascular Disease. | Allison, Criqui, Jenny, Budoff, Kalantar-Zadeh, Ix, McClelland, O'Connor, Carr | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | Lab, CC
A085 | Ventricular Size and Valve Calcification Measures by CT | Budoff, Katz, Obrien, Rotter. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | MESA CT RC, CC
A086 | Assessment of myocardial structure and regional LV function by echocardiography; A MESA Follow-up Study | Lima, Rosen, Fernandes, Chamera, Bahrami | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | JHU, CC
A087 | The Association of Celecoxib and Rofecoxib use with Endothelial Function in the MESA Cohort. | Allen, Herrington | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | WFU Reading Ctr
A088 | Hounsfield heterogeneity and location of coronary calcium for improved Cardiovascular Risk Prediction | Budoff, | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | 8/14/2008 | [5 empty] | Elizabeth Brown | Center: CT reading center with Dr. Budoff, MESA CC. (no FC) |  |  | CT reading center with Dr. Budoff, MESA CC. (no FC)
A089 | Risk factors for diastolic dysfunction measured by MR Imaging in MESA. | Qadir, Bluemke, Lima, Post. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [7 empty] | Center: MRI RC for the Exam 1 data - to be read onsite (will not leave the Reading Center) |  |  | MRI RC for the Exam 1 data - to be read onsite (will not leave the Reading Center)
A090 | Pulmonary vascular changes in early chronic obstructive pulmonary disease (“MESA-COPD”) | Barr, Bluemke, Enright, Hankinson, Hassoun, Hoffman, Kawut, Kronmal, Lima, Lui, Smith, Powell, Rabinowitz, Shimbo, Tracy, Watson. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | Columbia, JHU, NW, UCLA, MESA Core Lab, U Iowa Lung RC, MESA CC
A091 | Forsyth County Cohorts Study | Bertoni, Burke, Evans, Bell, Hairston, Rose. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | MESA CC (data preparation)
A092 | BK Viruria and Risk of Chronic Kidney Disease. | Johnson, Siscovick, Kestenbaum, Limaye, Corey. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | CC (sample selection)
A093 | The association between genetic variants of scavenger receptor class B type I (SR-BI) and lipids, subclinical atherosclerosis and cardiovascular events in MESA. | Rodriguez, Herrington, Post, Pollin | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | CC
A094 | The genetic basis of complex traits in natural populations of the house mouse. | Weir, Kronmal | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | CC
A095 | Candidate gene Association Resource (CARe) Study in the Multiethnic Study of Atherosclerosis (MESA). | Rotter, Gabriel, Boerwinkle, Rich, Heckbert., Post. | Per online report, study active status listed as 'Yes' (2/5/08, DV) |  |  | Yes | Yes | 1/1/2009 | [5 empty] | Sandi
A096 | SHARe (SNP Health Association Resource) Study in the Multi-Ethnic Study of Atherosclerosis | Rotter, Burke | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Yes | 7/1/2008 | [5 empty] | Craig
A097 | SPIROMICs natural history study of chronic obstructive pulmonary disease (COPD). | Barr, Kawut, Shea | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | Columbia
A098 | Interactions Between Diet and Genes Related to Risk of Type II Diabetes. | Nettleton, Jacobs (Sponsor), Boerwinkle, Hanus | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | No | [7 empty] | Per Craig, no data produced- study involves analysis only (2/7/08, DV) |  |  | none
A099 | Decline in Kidney Function and Incident Chronic Kidney Disease in a Multi-Ethnic Cohort. | Shlipak, Peralta, Siscovick, Katz, Kramer, Psaty, Kestembaum, De Boer, Cushman. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | Lab, CC
A100 | The MESA Kidney Study. | Shlipak, Siscovick, Watson, Palmas, Post, Coresh, Barr, de Boer, Stevens, Levey, Kramer. | Per online report, study active status listed as 'No' (2/5/08, DV) |  |  | No | Study Not Active Yet | [10 empty] | CC (data set prep); JHU, UCLA, Columbia
S01 | Sub-study: Microalbuminuria and changes in glomerular filtration rate (Kidney) | Kramer, Cooper, Liu, Cushman, Jacobs | MB & NHLBI approved 1/9/03. Grant submitted 2/1/03 not funded. Urine albumin/creatinine ratios will now be be measured as part of MESA parent study in visit 3. Abstract submitted to Nat'l Kidney Foundation. Awaiting final collection of Exam 3 data. | Participants w/o macroalbuminuria at baseline will be assessed for microabubminurea to study its association with CVD in a non-diabetic population. | 12/1/03 - 11/30/08 | Yes | Yes | 2006-01-31 |  | 2006-04-17 |  | 1 |  | Sandi | Previously listed as ancillary study A034 | MESAe3Lipids | vV3_RC_URINE | NU, Loyola, CC, Lab
S02 | Sub-study: Comparison of Dinamap- and mercury-measured blood pressure in MESA | Bild, Jinagouda, Kronmal, Liu, Ni, Proschan, Shea, Wu | Study activity listed as 'Completed' per online report (2/5/08, DV) ASC approved 12/2/03, SC approved 12/10/03. Training in early Jan. 2004; measurements Completedearly August 2004. Paper submitted for publication in June 2005. | During Exam 3, 50 ppts. from each FC will undergo three mercury BP measurements and three additional Dinamap BPs | 4/1/04 - 6/30/04 | Completed | Yes | 1/312004 |  | 2006-03-01 |  | 1 |  | Aruna |  | None-specific QC validation activity |  | All FCs, CC
S03 | FMD pilot reading study | David Herrington | Study activity listed as 'Completed' per online report (2/5/08, DV) Pilot Study approved by NHLBI July 2005. Readings CompletedFall 2005. Analyses and reports Completedlate 2005/early 2006. |  |  | Completed | Yes | 2007-09-01 |  | 2007-10-31 |  | 1 |  | Craig |  | MESAe1FMD | tRC_FMD | WFU
S04 | Serum Potassium Level and Subclinical Atherosclerosis | Homma, Nelson, Cushman, Tsai, Nelson, Kronmal, Shea | Per online report, study active status listed as 'Completed' (2/5/08, DV) |  |  | Completed | Yes | 9/1/2007 |  | 2007-09-01 |  |  |  | Norma |  | MESAe4BloodPotassium | vRC_Blood_Potassium | Columbia
Note on C23: Craig Johnson: Melissa Anderson and Felice Rando likely did the analyses published Spring 2004. Should check with them first.